## Ark1
Tasks |  |  |  | January | [19 empty] | February
Start date: 01.01.2021 |  |  |  | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16
| Duration | Recources | Progress
Analysis | 7 d | bar: January 14 to February 16
Requirement meetings | 2 d | PM & CW | bar: January 4 to January 5
Research/Current system | 4 d | PM, CW, DEV | bar: January 6 to January 11
Team kickoff meeting | 2 d | ALL | bar: January 12 to January 13
Planning/content | 9 d
Decide content hierarcy | 2 d | PM, CW | bar: January 14 to January 15
Create Sitemap | 2 d | PM, CW | bar: January 18 to January 19
Create content | 4 d | CW, PHOTO | bar: January 20 to January 25
Review content | 1 d | ALL | bar: January 26
Design | 8 d
Design wireframe | 2 d | CW, DEV | bar: January 27 to January 28
Design webpage | 5 d | DEV | bar: January 29 to February 4
Review webpage | 1 d | ALL | bar: February 5
Development | 14 d
Code webpages | 10 d | DEV | bar: February 8 to February 19
Initial testing | 2 d | DEV | bar: February 22 to February 23
Review meeting | 2 d | PM, DEV | bar: February 24 to February 25
Testing & Delivery | 11 d
Testing | 3 d | Hired | bar: February 26 to February 28
Correct issues | 4 d | DEV | bar: February 1 to February 4
Review meeting | 2 d | ALL | bar: February 5 to February 8
Delivery/Launch | 2 d | PM,DEV | bar: February 9 to February 10
Maintenance | 4 d
Review full site | 2 d | ALL | bar: February 11 to February 12
Update content | 2 d | CW,DEV | bar: February 15 to February 16